## Slide 1: Resource Scheduling Part 1
Project Management

## Slide 2: Brainsorming : The palm jumeirah, Dubai 2006

## Slide 3: Mega project of making a man-made island

## Slide 5: The questions
how much money spent?
How much sand spread out?
How many workers do we need?
How many ships used?
Are they used economically?

## Slide 6
Abundant resources make the project fast completion, but very costly (budget cost) and vice versa
Insufficient resources  over scheduleover budget
ahead-schedule
Over budget
Over schedule
Low budget
On time project

## Slide 7
Some resources are assigned to multiple tasks
Reallocated , adjusted, no longer overallocated
the overallocated resource works on tasks consecutively, instead of simultaneously.
Utilization and availability

## Slide 8
Resource scheduling is a tool for allocating the resources of project in economic terms
Human
cost
machine

## Slide 9: Why do we need?
As project managers, are given the finish date of the project before we even have a chance to plan for it (Domingues)
Schedules should be evaluated not merely in terms of meeting project milestones, but also in terms of the timing and use of scarce resources.

## Slide 10
the tasks will have to be rescheduled concurrently or even sequentially to manage the constraints
technological
resource
physical
Gray & Larson 2005
Nicholas

## Slide 11: relationship between time use and resource in resource allocation
  Resource Limited: The project must be finished as soon as possible, but without exceeding some specific level of resource usage or some general resource constraint
  Time Limited: The project must be finished by a certain time, using as few resources as possible. But it is time, not resource usage, that is critical

## Slide 12: Resource Leveling (Smoothing)
Resource leveling aims to minimize the period-by-period variations in resource loading by shifting tasks within their slack allowances.
The purpose is to create a smoother distribution of resource usage.
with a smooth increase at the beginning of a project and a smooth decrease at the end.

## Slide 13: The objectives of resource leveling
Resource leveling, referred to as resource smoothing, has two objectives:
To determine the resource requirements so that they will be available at the right time,
To allow each activity to be scheduled with the smoothest possible transition across usage levels

## Slide 14: 2 types of leveling resources
By delaying a task until the assigned resource has time to work on it.
By splitting a task so that part of a task is done when planned and the rest of it is done later when the assigned resource has time.

## Slide 15: example
normal
delayed
splitted

## Slide 16: Resource Levelling Heuristic
Resource management is a multivariate, combinatorial problem, i.e. multiple solutions with many variables, the mathematically optimal solution may be difficult or infeasible.
More common approach to analyzing resource leveling problems is to apply some resource leveling heuristics.

## Slide 17: The steps
List the accurate and complete WBS
Create a project activity network diagram
identify the most critical tasks
  By starting with the most important tasks first, the chance for successful project management is more likely

## Slide 18: The steps
Create a table showing the resources required for each activity, durations, and the total float available
Plot into gant chart
Check to see how many hours is available per team member for work then determine how many hours have been allocated to each person.

## Slide 19: The steps
If the number of hours allocated is above what is available they are over-allocated.
Develop a time-phased resource loading table
Identify any resource conflicts and begin to smooth the loading table using one or more heuristics

## Slide 20
Tasks should then be adjusted so that the number of required work hours are equivalent to the number of hours available.
Once this has been accomplished the critical project resources have been leveled. Next, do the same with the non-critical tasks.

## Slide 21: example
activity | predecessor | resource | duration
A | - | 6 | 4
B | A | 2 | 1
C | A | 2 | 3
D | B | 7 | 4
E | D | 3 | 2
F | E,C | 6 | 1
Resource limit is set at 8 hourly unit per day

## Slide 22: Draw project network

## Slide 23: Produce the table showing ES,LS EF,LF TF
activity | res | duration | ES | LS | EF | LF | TF
A | 6 | 4 | 0 | 0 | 4 | 4 | 0
B | 2 | 1 | 4 | 4 | 5 | 5 | 0
C | 2 | 3 | 4 | 4 | 11 | 11 | 4
D | 7 | 4 | 5 | 5 | 9 | 9 | 0
E | 3 | 2 | 9 | 9 | 11 | 11 | 0
F | 6 | 1 | 11 | 11 | 12 | 12 | 0
Critical path is A-B-D-E-F

## Slide 24: Plot into Gantt chart
Using dependency and interdependency diagram

## Slide 25
Resource imbalance

## Slide 26
Task splitted

## Slide 27: Resource Loading Chart
A
2
4
6
8
2
12
10
8
6
4
14
C
B
D
E
F
Project Days
Resources
Resource imbalance
Delayed task

## Slide 28: Summary
Period | Resource requirement | levelling
0-4 | 6 | 6
4-5 | 4 | 4
5-7 | 9 | 7
7-9 | 7 | 7
9-11 | 3 | 5
11-12 | 6 | 6